## Sprints
Sprint | Week | Sprint Goal | Start Date | End Date | Sprint State
- | 2/3 |  | 2022-10-24 | 2022-11-04 | Inactive
- | 4/5 |  | 2022-11-07 | 2022-11-18 | Inactive
- | 6/7 |  | 2022-11-21 | 2022-12-02 | Inactive
MST + Term Break
1 | 12/13 | To complete burglar detection, power management (high power mode and low power mode), physical payment by RFID reader, start up and main menu | 2025-07-02 | 2025-07-15 | Closed
2 | 14/15 | To modify how the raspberry pi dispenses drinks, create the remote access communication between vending machine and technician, authentication services when paying online and the end user website | 2025-07-16 | 2025-07-29 | Closed
3 | 16/17 | Both the hardware and software should feature math games. After each math game, they should be presented with a prize. All the hardware components should also be at a state of completion, where all of the requirements are satisfied. Should complete dockerising the container and push it to our remote docker repositories | 2025-07-30 | 2025-08-17 | Closed
Formulas:
End Date = [Start Date]+11
Start Date = [Start Date, row above]+14

## Active Sprint Board (hidden)
To Do | Doing | Done

## Product Backlog
ID | Story Title | Story Description | Definition of Done | Estimated Effort (hours) | Actual Effort (hours) | Status | Sprint
1 | Creation of SRS docs | As a Software Developer, I need to define all the different Use Case Diagrams for how the vending machine works and set the foundation | All necessary Use Case Diagrams are defined in the SRS document SRS document is commited and pushed to Github | 4 | 5 | Done | Sprint 1
2 | Develop Math Game for Website | Design and implement the interactive quiz game for customers to play while waiting for drinks. | When math quiz game works online. Successfully pushed into sprint 1. | 5 | 5 | Done | Sprint 1
3 | Setup Payment Integration | Implement QR code and RFID payment functionality for the vending machine. | When QR code and RFID payment works. Successfully pushed into sprint 1. | 8 | 10 | Done | Sprint 1
4 | Build Temperature Monitoring | Implement DHT11 sensor to monitor internal temperature and send email alerts when thresholds are breached. | When email received successfully.Successfuly pushed into sprint 2 branch | 7 | 8 | Done | Sprint 2
5 | Implement Burglar Detection | Configure IR sensor for tampering detection and set up the camera to send alerts to Telegram. | When telegram bot and email received successfully.Succesffuly pushed into sprint 2 branch | 8 | 8 | Done | Sprint 2
6 | Admin Mode Implementation | Implement admin login, passcode entry, and ability to edit stock. | When able to edit stock successfully and it goes int database. Successfully pushed into sprint 2 branch. | 6 | 7 | Done | Sprint 3
7 | Remote Access and Alerts | Implement remote access to monitor temperature and trigger alerts to staff. | When telegram bot and email received successfully.Succesffuly pushed into sprint 3 branch. | 5 | 8 | Done | Sprint 3
8 | System Testing and Debugging | Perform system testing to ensure all components work together seamlessly and fix any bugs. | All necessary pytest succeed and code fully integrated and working. Successfully pushed into sprint 3 branch | 7 | 12 | Done | Sprint 3
9 | Merging of codes | Merging sprint 1,2,3 codes into github | When all branches merged into master branch. | 1 | 2 | Done | Sprint 3
10 | Vetting of SRS doc, sprint planning and system test report. | SRS doc to be completed with the included requriements, test report for pytest and rpi. | when all docs completed. | 2 | 4 | Done | Sprint 3
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95 | [5 empty] | Doing
96
97
98
99
100

## enum (hidden)
Sprint | Start Date | End Date | Story Status | Spint State
Sprint 1 |  |  | To Do | Inactive
Sprint 2 |  |  | Doing | Active
Sprint 3 |  |  | Done | Closed
Sprint 4
Sprint 5
Sprint 6